**PROPOSAL**

**Manatee Protection Project**

**Continuation**

**City of Jacksonville**

**Duval County, Florida**

**October 1, 2020 - September 30, 2021**

Prepared by:

A. Quinton White, Jr., Ph.D.

Gerard Pinto, Ph.D.

Jacksonville University

Jacksonville, FL 32211

**I. General Information:**

Request for Proposal from: City of Jacksonville, Florida Waterways Commission

Subject: Maintaining a Comprehensive Database for a Manatee Management Protection Plan and Manatee Awareness Program; Consultant to Waterways Commission on Water related matters

Location: Duval County, Florida

**II. A - Background and General Information:**

This proposal is to continue the contract to maintain the comprehensive database for the Duval County Manatee Protection Plan that was approved by the State of Florida. This proposal is for the period of October 1, 2020, to September 30, 2021.

The City of Jacksonville has embarked on a focused vision to activate the St. Johns River with extensive effort to promote development and increase boating activity on the St. Johns River. The Florida Manatee (Trichechus manatus) is Florida’s state marine mammal and is a significant concern to the people of Duval County, as well as the entire state. Throughout Florida, the manatee, which is protected under state and federal law, has suffered increasing mortality with the majority of the deaths repeatedly related to boating activities. Northeast Florida, including Duval County, has shown a general decline in manatee deaths over the past several years.

The St. Johns River provides habitat for the manatee along with supporting tremendous recreational and industrial use. Boat traffic in the river is very diverse. It includes port facilities for large industrial and commercial shippers, commercial fishing, sport fishing and recreational activity. More than 200 large commercial boats/ships per month enter and exit the mouth of the St. Johns River in Duval County with the number expected to increase over the next decade with the possible deepening of the port channel. These vessels represent a significant economic factor for Duval County and the entire First Coast-. In addition, there are almost 30,000 recreational boats registered in Duval County.

A wide range of manatee usage of the St. Johns River has been observed. Manatees are most often seen traveling or moving from one location to another. Manatees were also observed feeding, cavorting/mating and resting. Distribution varies throughout the year with sightings of manatees during the late winter season being uncommon. Manatee abundance in Duval County waters increased during the spring and peaked during the late summer (Valade 1991, White 2002). Jacksonville University has conducted additional studies to build a significant database to be used to develop a Manatee Management Plan.

The large amount of boating activity on the St. Johns River and the number of manatees that has -been documented using the river make it critical that a comprehensive management plan for the waters of Duval County be enacted to protect both manatee and human activity. We have been accumulating information on the manatee usage of the St. Johns River in an effort to provide a complete database and foundation for a comprehensive management plan. Several areas of research are necessary to continue to document the habitat, manatee usage and human usage of the St. Johns River.

Jacksonville University has been gathering existing information concerning manatee behavior and natural history, including studies performed by various state, county and city agencies, along with universities and consultants. Studies on boaters including industrial, commercial sport and commercial fishing and recreation have also been included in the database.

Although a diverse amount of information exists concerning the manatee, very little information exists on the effects of boating on the manatee population. This proposal will expand the Manatee Awareness Program and examine boating activity on manatee behavior.

**II B. Description of Project:**

This proposal outlines a “Scope of Services” for the continuation of the Manatee Protection Plan. The study/project is to continue to assemble and analyze an information database in order to update the management plan so that it continues to provide adequate protection for all concerned. In addition, public support of the plan can be enhanced through education and input from concerned citizens and industries.

In addition, this proposal includes environmental consulting services to the Waterways Commission on water-related issues concerning the St. Johns River, its tributaries and near-shore waters of the Atlantic Ocean. Any additional scope of services can be negotiated on a per-need cost basis.

**III. Scope of Work:**

**2020-2021**

**JU Manatee Contract Deliverables**

**TASK 1 Support Jacksonville Waterways Commission - monthly**

Provide monthly updates on manatee research, artificial reefs and water-related issues in Duval County. At the end of the year, summarize manatee information discussed during the year.

**TASK 2 Continuation of Manatee Sighting – 3 times per year**

Continuation of manatee sighting flights for the county by aerial surveillance to determine movement patterns of manatees. This information will be collected using surveys conducted approximately three times a year, with additional flights when possible.

**TASK 3 Waterways/ Manatee Information Signage Inventory – update database**

Jacksonville University will update database of all local manatee, boating-safety signage and information kiosks at boat ramps in Duval County to maintain current -information. This will include all commercial and multi-family marinas and docks and all manatee information signs and kiosks. Provide database to City at the end of the contract year.

**TASK 4 Community Education Efforts- Report efforts quarterly**

JU will report to COJ a summary of educational efforts quarterly.

A. If requested, JU will work with the COJ, JSO, FWC, and FWS LE to develop a pamphlet to be distributed via boat facilities and/or mail outs. Pamphlets will include boating safety and manatee protection zones. JU is not responsible for printing and mailing of brochure.

.

B. Work with the NE Florida Regional Council and its partners to increase

manatee awareness

C. Explore and develop new education and awareness programs

D. Maintain JU website, ju.edu/MARCO

E. Track number of calls to JU Manatee Hot Line

F. Keep PowerPoint presentation up to date for educational programing.

**TASK 5 Port Education/Awareness Reporting – Report quarterly**

Work with port entities to track level of shipping activity, determine which of the manatee efforts are working, and assist in making their manatee

programs effective

B. Work with JMTX to educate commercial ships operators about manatee safe-docking procedures

C. Work with JMTX to decrease incidents of large ships displacing or destroying waterway signage

D. Attend JMTX Harbor Safety Committee as necessary

**TASK 6 Law Enforcement Efforts – Report quarterly**

A. Through the Law Enforcement Task Force, work with JSO to provide

the information requested by USFWS and in the format acceptable to

the agency.

B. Track law enforcement-efforts -to direct JSO to target

certain areas in order to use resources efficiently and effectively

C. Attend COJ Law Enforcement Task Force meetings as necessary

D. At the end of the year, summarize law enforcement activities and make

recommendations for increased coordination and communication

**TASK 7 Update marine facility inventory**

Provide COJ with updated marine facility inventory database of all facilities with five more slips in Duval County, indicating any significant changes in 2018-2019. Database will include:

A. List of all marinas – wet and dry storage, public and private and multi-

family

B. Number of slips and percentage of occupancy

C. List of all boat ramps and number of parking spaces and launch lanes

D. List of all commercial facilities and number of slips

E. Provide database to the City.

**TASK 8 – Continuation of Boater Speed Zone Compliance Study**

Conduct the boater speed zone compliance study based on protocols agreed upon with FWC. The study will be conducted for one (1) year at various locations, days and times throughout the year. This task is being extended through this contract year due to COVID. At the end of the year, provide a report of activities, summarize data and make recommendations. Cost Task 8, the Boater Speed Zone Compliance Study, will be $90,000 above and beyond the yearly $90,000 yearly contract. Funding for the Boater Speed Zone Compliance Study will be carried over from the 2019-2020 contract through an existing Purchase Order

**TASK 9 MPP Implementation Report – Provide report at end of the year**

Compile and write yearly implementation summary report due to FWC. Analyze and summarize all MPP data collected and compare protection and education efforts to past years. Report will include but is not limited to the following tasks:

A. All manatee education presentations provided by COJ, JU, and JSO

Documented items will include:

1. The number and type of presentations

2. Type of group: public or private

2. The intensity of use of various educational materials

3. Some gauge of public reception

4. Any other details that may allow for manatee awareness

program effectiveness evaluation.

B. Manatee Mortality Data – Provide to COJ end of the year report/maps

C. Manatee Habitat Resource Map - Provide to COJ updated GIS map

D. Summarize JSO law-enforcement efforts based on JSO reports and

input.

E. Make recommendations on all MPP implementation tasks.

**IV. Budgetary Schedule**

Funding of this project is a fixed fee of $180,000. Both JU benefits costs and flight costs have increase for the next year. The budget includes all specific objectives, all consultant’s fees, direct labor, benefits (30%), travel, materials, aerial survey and overhead (10%). Any additional services will be negotiated on an as-needed basis.

**V. Insurance Requirements:**

Jacksonville University shall procure and maintain during the entire life of this agreement insurance of the types and in the minimum amounts as required by the City of Jacksonville.

**VI. Fee Submittal:**

# Invoices will be submitted monthly and are payable upon receipt by the City of Jacksonville.

# JU Manatee Study - Insurance Requirements

Without limiting its liability under this agreement, the Consultant and/or its sub-consultants shall procure and maintain at their sole expense, during the term of the project, insurance of the type and in the minimum amount stated below:

## SCHEDULE LIMITS

Workers Compensation Florida Statutory Coverage

Employer's Liability $100,000 Each Accident

(including appropriate Federal Acts) $500,000 Disease Policy Limit

$100,000 Each Employee/Disease

Commercial General Liability $2,000,000 General Aggregate

Premises- Operations $2,000,000 Products/Comp. Ops. Agg.

Products- Completed Operation $1,000,000 Personal/Advertising Injury

Contractual Liability $1,000,000 Each Occurrence

Independent Contractors $50,000 Fire Damage

$5,000 Medical Expenses

(The City of Jacksonville shall be named as an additional insured under a/l of the above Commercial General Liability coverage)

Automobile Liability. $1,000,000 Combined Single Limit

(All Automobiles-Owned, Hired or Non-owned)

Professional Liability $1,000,000

(Professional Liability coverage will be provided on an Occurrence Form or a Claims made Form with a retroactive date equal to at least the first date of this agreement and with a three year reporting option beyond the annual expiration date of the policy)

Aircraft Liability $1,000,000

(The City of Jacksonville shall be named as an additional insured under Aircraft Liability coverage)

Watercraft Liability (Protection and Indemnity) $1,000,000

(The City of Jacksonville shall be named as additional insured under the Watercraft Liability coverage)

Depending on the nature of the work required in this project and its accompanying exposures and liabilities, the CITY may, at its sole option, require additional security instruments (e.g. bonds) and insurance coverage of the types and in the amounts responsive to those liabilities which may or may not require the CITY also be named as an additional insured.

Said insurance shall be written by an insurer holding a current certificate of authority pursuant to chapter 624, Florida Statutes. Such insuranceshall be endorsed to provide for a waiver of underwriter's rights of subrogation in favor of the City. Such insurance shall be written by an insurer with an A. M. Best Rating of A X or better. Prior to commencing any work on the project, Certificates of Insurance approved by the City's Division of Insurance & Risk Management evidencing the maintenance of the required insurance shall be furnished to the City. The certificates shall provide that no material alteration or cancellation, including expiration and non-renewal shall be effective until thirty (30) days after receipt of written notice by the City.

Anything to the contrary notwithstanding, the liabilities of the Consultant under this Agreement shall survive and not be terminated, reduced or otherwise limited by any expiration or termination of insurance coverages. Neither approval nor failure to disapprove insurance furnished by the consultant shall relieve the consultant or its subconsultants from responsibility to provide insurance as required by the contract.

### Manatee Protection Plan

### Baseline Study Budget

**Direct Labor**

Salaries $60,000

Senior Scientist ($ 9,000)

Research Scientist ($51,000)

Benefits @ 30% of Direct Labor $ 18,000

$ 78,000

**Travel** $ 500

**Material and Supplies** $ 500

**Aviation** $2,800

Subtotal $81,800

**Overhead** - 10% of Subtotal $ 8,200

Total $90,000

**Boater Speed Zone Compliance Study** $90,000

Funding for the Boater Speed Zone Compliance Study will be carried over from the 2019-2020 contract through an existing Purchase Order

**Note:** Benefits to include, as appropriate, social security, medical insurance and retirement contributions.